Quotation and cost estimate: Plan 3 Open-Plan Contemporary

| Quotation no. | Date | Valid until | Client / project | Quality | Region |
| --- | --- | --- | --- | --- | --- |
| QT-20261028-0002-P3 | 28 Oct 2026 | 27 Nov 2026 | Home build | Standard | Tier-2 city |

Built-up area 528 sq ft over 2 floor(s) on a plot of 442 sq ft (26'-0" x 17'-0").

| No. | Description | Unit | Qty | Rate | Amount |
| --- | --- | --- | --- | --- | --- |
|  | A. MAIN BUILDING (CIVIL AND FINISHING) |  |  |  |  |
| 1 | Excavation, footing, plinth beam and filling - RCC M25 footings, PCC bed, anti-termite treatment | sq ft | 528 | Rs. 214 | Rs. 1,12,992 |
| 2 | RCC structure: columns, beams and slabs - Fe500D steel, M25 concrete, quality shuttering | sq ft | 528 | Rs. 468 | Rs. 2,47,104 |
| 3 | Brick / block masonry - 9 in outer + 4.5 in inner walls, AAC / clay blocks | sq ft | 528 | Rs. 156 | Rs. 82,368 |
| 4 | Plastering (internal and external) - Cement plaster with sponge / putty finish | sq ft | 528 | Rs. 117 | Rs. 61,776 |
| 5 | Flooring, tiling and skirting - Vitrified / porcelain / wooden / anti-skid by room | sq ft | 528 | Rs. 214 | Rs. 1,12,992 |
| 6 | Doors and windows - Teak main door, flush / solid doors, UPVC / aluminium with glass | sq ft | 528 | Rs. 156 | Rs. 82,368 |
| 7 | Electrical works - Concealed copper wiring, modular switches, MCB / DB panel | sq ft | 528 | Rs. 117 | Rs. 61,776 |
| 8 | Plumbing and sanitary - CPVC / UPVC pipes, branded sanitaryware & CP fittings | sq ft | 528 | Rs. 117 | Rs. 61,776 |
| 9 | Painting and finishing - Acrylic putty, primer, emulsion interior + weather-coat exterior | sq ft | 528 | Rs. 98 | Rs. 51,744 |
| 10 | Waterproofing and roof finishing - Terrace, bathroom & wet-area waterproofing system | sq ft | 528 | Rs. 58 | Rs. 30,624 |
| 11 | Staircase and railing - Granite / marble treads, SS / glass / designer railing | sq ft | 528 | Rs. 58 | Rs. 30,624 |
| 12 | Kitchen platform, modular units and wardrobes - Granite / quartz platform, modular base units, loft & wardrobes | sq ft | 528 | Rs. 98 | Rs. 51,744 |
| 13 | Miscellaneous finishing and cleaning - Grills, hardware, false ceiling allowance, final cleaning | sq ft | 528 | Rs. 78 | Rs. 41,184 |
|  | B. SITE WORKS AND EXTERNAL DEVELOPMENT |  |  |  |  |
| 14 | Compound wall 5 ft high with plaster and paint | rft | 76 | Rs. 1,400 | Rs. 1,06,400 |
| 15 | Main gate and pedestrian gate (MS / designer) | lump | 1 | Rs. 45,000 | Rs. 45,000 |
| 16 | Driveway and paving | sq ft | 30 | Rs. 140 | Rs. 4,200 |
| 17 | Garden: lawn, beds, trees, gazebo and irrigation | sq ft | 136 | Rs. 110 | Rs. 14,960 |
| 18 | Terrace garden: waterproofing, planters, pergola, grow-beds | sq ft | 102 | Rs. 320 | Rs. 32,640 |
| 19 | Underground sump, overhead tank and borewell connection | lump | 1 | Rs. 60,000 | Rs. 60,000 |
| 20 | Rain-water harvesting pit and drainage | lump | 1 | Rs. 25,000 | Rs. 25,000 |

Summary

| Item | Amount |
| --- | --- |
| A. Main building | Rs. 10,29,072 |
| B. Site works and external development | Rs. 2,88,200 |
| Sub-total (A + B) | Rs. 13,17,272 |
| Architect and structural design fee (3%) | Rs. 39,518 |
| Approvals, permits and utility connections (1%) | Rs. 13,173 |
| Contractor overhead, profit and supervision (8%) | Rs. 1,05,382 |
| Contingency (5%) | Rs. 65,864 |
| GST at 18% on design and contractor service charges | Rs. 26,082 |
| GRAND TOTAL ESTIMATE | Rs. 15,67,291 |
| Cost per sq ft of built-up area | Rs. 2,968 |
| Estimated construction time | 8 months |

Amount in words: Fifteen lakh sixty-seven thousand two hundred ninety-one rupees only.

Payment schedule (milestone billing)

| Stage | Share | Amount |
| --- | --- | --- |
| Advance / booking | 10% | Rs. 1,56,729 |
| Foundation and plinth complete | 15% | Rs. 2,35,094 |
| Columns, beams and slabs complete | 25% | Rs. 3,91,823 |
| Masonry and plastering complete | 15% | Rs. 2,35,094 |
| Flooring, doors and windows complete | 15% | Rs. 2,35,094 |
| Electrical, plumbing and painting complete | 15% | Rs. 2,35,094 |
| Handover and final snag clearance | 5% | Rs. 78,365 |

Total cost by finish quality (same plan)

| Quality | Total estimate | Per sq ft |
| --- | --- | --- |
| Standard | Rs. 15,67,291 | Rs. 2,968 |
| Premium | Rs. 21,79,961 | Rs. 4,129 |
| Luxury | Rs. 29,74,414 | Rs. 5,633 |

Terms and conditions

•  This is an indicative budget estimate for planning. A final quotation needs site soil test, structural design and approved drawings.

•  Rates follow the selected finish quality and region and may change with material prices, labour and city rules.

•  Quotation is valid for 30 days from the date shown. Rates after that are subject to revision.

•  Excluded: land cost, registration, furniture, appliances, interior decoration, lifts, solar power and landscaping beyond the items listed.

•  Payment is stage-wise as per the schedule. Extra work outside this scope is charged separately.

•  GST shown applies to design and contractor service charges; material GST is already inside the item rates.

Prepared by: Home Planner        Client signature: ______________________        Contractor signature: ______________________